## Gantt Chart
Microsoft C# Kernel Group Gantt Chart
Task Name | Start Date | End Date | Duration (Days) | Days Complete | Days Remaining | Percent Complete(Days) | Comments | Team | Completion
Get C# Kernel Environment on Mac/Windows | 2018-05-13 | 2018-05-19 | 6 | 3 | 3 | 50% | Windows Done | A, B, C | 50%
Syntax Highlighting | 2018-05-19 | 2018-06-01 | 13 | 0 | 13 | 0% |  | B | 0%
Errors | 2018-05-19 | 2018-05-25 | 6 | 0 | 6 | 0% |  | C | 0%
Intellisense | 2018-05-25 | 2018-05-31 | 6 | 0 | 6 | 0% |  | A | 0%
C# Notebooks Structure | 2018-05-25 | 2018-05-27 | 2 | 0 | 2 | 0% |  | B,C | 0%
C# Notebooks Implementation | 2018-05-27 | 2018-06-04 | 8 | 0 | 8 | 0% |  | B,C | 0%
Testing Kernel | 2018-06-01 | 2018-06-06 | 5 | 0 | 5 | 0% |  | A | 0%
Testing Kernel + Notebook | 2018-06-01 | 2018-06-06 | 5 | 0 | 5 | 0% | Testing Kernal Exclusive w/ Notebook | A, B, C | 0%
Leaflet (10%) | 2018-06-04 | 2018-06-09 | 5 | 0 | 5 | 0% |  | A, B, C | 0%
Hackbooth (50%) | 2018-06-08 | 2018-06-14 | 6 | 0 | 6 | 0% |  | A, B, C | 0%
Documentation (25%) | 2018-05-13 | 2018-06-27 | 45 | 0 | 45 | 0% | Git Repository | A, B, C | 0%
Peer Assessment (5%) | 2018-06-14 | 2018-06-27 | 13 | 0 | 13 | 0% |  | A, B, C | 0%
Portfolio (10%) | 2018-05-13 | 2018-07-09 | 57 | 0 | 57 | 0% | Individual | A, B, C | 0%
Tasks | Team A | Team B | Team C |  | Team A | Team B | Team C
Get C# Kernel Environment on Mac/Windows |  |  |  |  | Mostafa | Mwana | Andre
Syntax Highlighting |  |  |  |  | Mohamed | Thanos | James
Errors | [5 empty] | Omer
Intellisense
C# Notebooks Structure
C# Notebooks Implementation
Testing Kernel
Testing Kernel + Notebook
Leaflet (10%)
Hackbooth (50%)
Documentation (25%)
Peer Assessment (5%)
Portfolio (10%)